SP-EU Stage 2 Timeline

2024-01-06

# Email

Please start all emails in the subject heading with [Sp-EU]

# Timeline – 11 weeks

We do have 11 weeks in front of us until submission. Each week has a main goal to be accomplished related to a specific part of the proposal.

| Week | Start Date | Events/Content | Main Goal |
| --- | --- | --- | --- |
| 0 | 24.01. | Call Opening | Timeline |
| 1 | 29.01. | 5 workshops on the proposal parts | Content of stage 1 into templates |
| 2 | 05.02. | Specific tasks preparing workshop | First draft Excellence |
| 3 | 12.02. | Specific tasks preparing workshop | First draft Impact |
| 4 | 19.02. | Workshop in Berlin | First draft Quality and Efficiency |
| 5 | 26.02. | Site visits | Final draft Excellence |
| 6 | 04.03. | Site visits | Final draft Impact |
| 7 | 11.03. |  | Final draft Quality and Efficiency |
| 8 | 18.03. | Site visits | Finishing Excellence |
| 9 | 25.03. |  | Finishing Impact |
| Easter |  |  |  |
| 10 | 01.04. |  | Finishing Quality and Efficiency |
| 11 | 08.04. |  | Submission |

# Weekly Briefings

We will start each week with a briefing about the week’s contents and goals at Monday 10am CET / 9am GMT.

# Proposal outline (max. 50 pages)

- Excellence  (around 18 pages)

Excellence – aspects to be taken into account. - Clarity and pertinence of the project’s objectives, and the extent to which the proposed work is ambitious, and goes beyond the state of the art. - Soundness of the proposed methodology, including the underlying concepts, models, assumptions, interdisciplinary approaches, appropriate consideration of the gender dimension in research and innovation content, and the quality of open science practices, including sharing and management of research outputs and engagement of citizens, civil society and end users where appropriate.

  - Objectives and ambition [e.g. 4 pages]

  - Methodology [e.g. 14 pages]

- Impact (9 pages)

Impact – aspects to be taken into account. - Credibility of the pathways to achieve the expected outcomes and impacts specified in the work programme, and the likely scale and significance of the contributions due to the project. - Suitability and quality of the measures to maximise expected outcomes and impacts, as set out in the dissemination and exploitation plan, including communication activities

2.1		Project’s pathways towards impact [e.g. 4 pages]

2.2	Measures to maximise impact - Dissemination, exploitation and communication #@COM-DIS-VIS-CDV@# [e.g. 5 pages, including section 2.3]

2.3 Summary (Canvas)

3.	Quality and efficiency of the implementation (22 pages)

Quality and efficiency of the implementation – aspects to be taken into account - Quality and effectiveness of the work plan, assessment of risks, and appropriateness of the effort assigned to work packages, and the resources overall - Capacity and role of each participant, and extent to which the consortium as a whole brings together the necessary expertise.

3.1	Work plan and resources [e.g. 19 pages for topics using lump sum funding  – including tables]

3.2	Capacity of participants and consortium as a whole [e.g. 3 pages]

ANNEX: Clinical Trials Template (around 20 pages)

# Workshop

We will conduct a workshop in Berlin at Feb 19th and 20th at Charité Campus Mitte next to the main station.

Main goals:

- Teambuilding: We will get to know each other in person, and also make a photo which we might use for the proposal

- Talking through each step of the SP-EU project jointly to find all pitfalls and misunderstandings and have a good plan to conduct SP-EU

- To include the perspective of the three vulnerable groups taregeted by a session each with representatives

Part of the workshop will be hybrid, part only in presence.

In the evening of Feb 19th, we will have an informal get together.

Every site should have a representative taking part.

Please register in any case at https://forms.office.com/e/9ThUcC7UXh until Jan 31st.

# Site Visits

Wolfram will visit every site to get to know the people and the conditions there in planning SP-EU.