SP-EU Workshop 19./20.02.2024

Status 14.02.2024

We are very happy to welcome you to Berlin for our workshop to prepare the full proposal for SP-EU.

# Goals of this workshop

- To build a team which is able and willing to prepare the proposal and conduct the project successfully together

- To create a joint understanding of work packages and tasks involved

- To refine the work plan of the project

- To discuss crucial aspects for a successful implementation of the project

# Plans

# Day 1 February 19th

9:00-9:15 	Goals of workshop and SP-EU

Aim: Set a foundation for the workshop

9:15-10:00	Introduction and get to know each other (hybrid: Click here to join the meeting)

Aim: Become familiar with each other and become a team

10:00-10:45	Lump Sums and Work Packages – Project management aspects of the proposal incl. Time for Questions (hybrid: Click here to join the meeting)

Aim: Set the technical foundation to understand work packages and funding

10:45-11:00	Coffee Break

11:00-12:00	KERs and necessary tasks (Group Work)

Aim: Look out for missing tasks and how to organize tasks best

12:00-12:45	Lunch

12:45			Group Photo

12:55-13:45	Group Work with three parallel groups

Co-Creation 1st phase;

Aim: Discuss the step-by-step procedure to conduct the co-creation process in 1st year

Digital tool development;

Aim: Discuss requirements for the tool

Ethics and Data security

Aim: Collect requirements in different countries and hubs involved

13:45-14:30	RCT Overall design (hybrid: Click here to join the meeting)

Aim: Create a shared understanding of the overall RCT design including preparation, study site initiation,  baseline, follow up 6M FU 12M

14:30			Coffee break

15:00-16:00	Consultation with representatives of refugees and first-generation immigrants

Aim: Which topic should be addressed in adapting SP? What shall we take in mind in planning the RCT?

[Alternative: Discussion on language support for data acquisition and intervention delivery]

16:00-16:45	RCT Intervention delivery (hybrid: Click here to join the meeting)

Aim: Talk through the details of the intervention delivery

16:45-17:30	RCT Outcome Measurement (hybrid: Click here to join the meeting)

Aim: Discuss how to measure the primary outcome

18:00			Dinner at Hummus and Friends

# Day 2 February 20th

9:00-9:15	Welcome and morning round

9:15-10:00	Communication, dissemination, exploitation, policy (hybrid: Click here to join the meeting )

Aim: What do we need? Stakeholders, channels, materials, measures

10:00-10:45	Additional partners and advisory boards: Advisory, Implementation, Patient Board and Data Monitoring Committee (hybrid: Click here to join the meeting)

Aim: Which forms and whom to include?

11:00-12:00	Consultation with representatives of LGBTI persons (hybrid: Click here to join the meeting)

Which topic should be addressed in adapting SP? What shall we take in mind in planning the RCT?

12:00-12:45	Lunch

12:45-13:45	Consultation with representatives of older persons

Which topic should be addressed in adapting SP? What shall we take in mind in planning the RCT?

13:45-14:15	Coffee break

14:15-15:00	Sum Up

15:00		End

# Participants

## In Berlin on site

- Stéphanie B (Bern) [arriving Monday noon]

- Moa (Bern) [arriving Monday noon]

- Hendrik (Berlin)

- Wolfram (Berlin)

- Philip (Berlin)

- Stephanie R (Berlin)

- Lilian (Berlin)

- Thomas K (Hamburg)

- Thomas Z (Hamburg)

- Claudia (Freiburg)

- Kerryn (Plymouth)

- Sine (Aalborg)

- Juliane (Wuppertal)

- Sibylle (Active Group)

- Jelena (Zagreb)

- Iva (Zagreb)

- Ana (Lisbon)

- Maria (Lisbon)

- Andrea (Concentris) [only on Monday]

## Online

- Lina (Eurohealthnet)

- Alison (Eurohealthnet)

- Stephanie (Oxford)

- Sónia (Lisbon)

- Donata (Wroclaw)

- Merrick (Toronto)

- Nicola (Catalonia)

- Daniela (Vienna)

- Emmily (Ghent)