| Nr | Title | Begin | End | Reporting after | Lead | Partners with funding | Objective | Tasks (Aim 2-4/WP) | Deliverables |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Coordination, Project and Data Management 1 | 1 | 12 | 12 | Charité | Concentris | Facilitate the optimal joint work of the consortium and all partners to reach an optimal performance during the project | T1 Establish project governance structure T2 Enhance scientific collaboration T3 Write Data Management Plan T4 Conduct risk, quality and ethics monitoring T5 Contract management, reporting and finan | Data Management Plan |
| 2 | Coordination, Project and Data Management 2 | 13 | 30 | 30 | Charité | Concentris | Ensure a collaborative execution of the project with minimized risks | T1 Establish patient advisory board and independent data monitoring committee T2 Enhance scientific collaboration T3 Data management T4 Conduct risk, quality and ethics monitoring T5 Contract management, reporting and financial management | Midterm report on ethics and risk monitoring |
| 3 | Coordination, Project and Data Management 3 | 31 | 48 | 48 | Charité | Concentris | Ensure a collaborative execution of the project with minimized risks - KER7 | T1 Enhance scientific collaboration T2 Data management T3 Conduct risk, quality and ethics monitoring T4 Contract management, reporting and financial management | Update of data management plan |
| 4 | Coordination, Project and Data Management 4 | 49 | 60 | 60 | Charité | Concentris | Enable triangulation of results and public availability of all results - KER4.1 | T1 Enhance scientific collaboration bringing the results of all project parts together for triangulation T2 Data management incl. publication of all project data T2 Conduct risk, quality and ethics monitoring T3 Contract management, reporting and financial management | Report on status of posting all project data |
| 5 | Cocreation of Social Prescribing Intervention | 1 | 12 | 12 | Aalborg | All RCT-Hubs | Cocreate the social prescribing intervention with representatives of the three vulnerable groups - KER1 | T1 Conduct Evidence Review and consult key stakeholders along with representatives of each vulnerable group T2 Co-create an adaptation of SP T3 Prototype the intervention with people of each group | Report on cocreation workshops with each group |
| 6 | Digital Tool Development | 1 | 18 | 30 | ActiveGroup |  | Develop a web-based open-source technical solution, which will help link workers assemble, curate, and classify a list of local offerings by scraping public GIS sources | T1 Develop the tool T2 Write a documentation of the technical solution | Documentation of web-based open-source technical solution to support adapted SP |
| 7 | Digital Tool Support | 19 | 42 | 48 | ActiveGroup |  | Support the use of the digital tool during the implementation in the trial and prepare a sustainable use afterwards - KER 4.2 | T1 Support link workers using the tool during the interventions T2 Develop and publish a publicly available version of the tool | Report on support of web-based open-source technical solution to support adapted SP |
| 8 | Ethics and Trial Preparation | 1 | 18 | 30 | Charité | All RCT-Hubs | Prepare all necessary documents and steps to assess the effectiveness of SP in a randomized-controlled trial | T1 Compile trial documents for patients, hubs and sites T2 Develop training program for link workers, hubs and sites T3 Get ethics approvals for all hubs and sites T4 Develop a data security plan | Study Initiation Packages Incl. Ethics Deliverables |
| 9 | Trial Implementation 1 | 19 | 30 | 30 | Charité | All RCT-Hubs Plymouth | Conduct successfully a pragmatic international multicentre randomized controlled basket trial to assess the effectiveness of SP | T1 Initiate Hubs T2 Train link workers T3 Initiate sites T4 Recruit patients T5 Baseline data acquisition and randomization T6 Intervention delivery T7 Supervision of link workers | Midterm recruitment report |
| 10 | Trial Implementation 2 | 31 | 48 | 48 | Charité | All RCT-Hubs Plymouth | Conduct successfully a pragmatic international multicentre randomized controlled basket trial to assess the effectiveness of SP | T1 Recruit patients T2 Baseline data acquisition and randomization T3 Intervention delivery T4 Supervision of link workers T5 6 Months Follow Up T6 12 Months Follow Up T7 Site closure | Final recruitment report |
| 11 | Trial Analysis | 43 | 60 | 60 | Charité |  | Analyse the trial data to assess the effectiveness of SP to improve access to health-related parts of social care systems - KER2 | T1 Write statistical analysis plan T2 Data cleaning T3 Analysis of primary end-point T4 Analysis of secondary endpoints and sensitivity analyses T5 Individual patient data meta-analysis T6 Prepare trial data for anonymized publication | Report on the status of posting RCT results |
| 12 | Trial Process Evaluation | 13 | 48 | 48 | Plymouth | Oxford | Evaluate the fidelity and quality of the implementation of SP in the trial | T1 Conduct participant observation T2 Conduct qualitative interviews with actors involved in trial T3 Analyse qualitative data T4 Analyse quantitative process data | Report on fidelity and quality of implementation |
| 13 | Health Economics Assessment | 13 | 60 | 60 | Wuppertal |  | Conduct health economic analysis regarding SP based on the trial data | T1 Develop a health economics framework for SP T2 Analyse health economics data from the trial T3 Develop a framework for sustainable financing of SP in Europe | Framework for sustainable financing of SP in European countries |
| 14 | Qualitative Comparative Study | 13 | 48 | 48 | Oxford | All Quali-Hubs | Explore enabling and limiting factors to implement SP as a solution to improve access to health and care services for people in vulnerable situations - KER3 | T1 Conduct approximately 20 stakeholder interviews in each of the five countries and transcribe them verbatim T2 Develop summaries (in a table-like chart) of what participants said in an interview, which can be shared with members of the research team T3 Develop a thematic framework to chart data against and produce six charts T4 Apply the framework of policy cost-effectiveness | Report on implementing the qualitative comparative study in five European countries |
| 15 | Cointerpretation of results | 49 | 60 | 60 | open | Cocr Leads | Interpret the results of the different parts of SP-EU together with representatives of vulnerable groups - KER6 | T1 Results of the RCT and of the qualitative comparative part are going to be interpreted jointly by researchers and representatives of all three groups of people in vulnerable situations T2 Combine the experiences regarding the co-creation process into a manual | Manual on co-creation in European health care interventions |
| 16 | Communication, Dissemination, Exploitation, Policy 1 | 1 | 12 | 12 | NASP | Eurohealthnet, Concentris | Prepare the field for an optimal communication and dissemination throughout the whole project | T1 Identify target groups for the communication of SP-EU together with all partners and representatives of vulnerable groups T2 Develop a corporate design for SP-EU T3 Identify communication channels to be used | Plan for the dissemination and exploitation of results including communication activities |
| 17 | Communication, Dissemination, Exploitation, Policy 2 | 13 | 30 | 30 | NASP | Eurohealthnet, Concentris | Set up all communication channels needed for communication, dissemination and exploitation | T1 Set up a webpage including a knowledge hub T2 Set up social media channels for SP-EU T3 Identify and approach key stakeholders for dissemination and exploitation | Report on web page and social media set up and performance |
| 18 | Communication, Dissemination, Exploitation, Policy 3 | 31 | 48 | 48 | Eurohealthnet | NASP, Concentris | Connect with policy makers to prepare the dissemination and exploitation of the project results | T1 Develop an initial exploitation plan T2 Communicate results from the different work packages | Initial Exploitation Plan |
| 19 | Communication, Dissemination, Exploitation, Policy 4 | 49 | 60 | 60 | Eurohealthnet | NASP, Concentris | Enable the full exploitation of all key exploitable results of SP-EU to reach the maximum impact - KER5 | T1 Conduct one policy roundtable in eight EU countries for decision- and policy makers, providers, health and care workers on how to sustainably implement SP for people in vulnerable situations T2 Conduct one EU-level roundtable (e.g., in the European Parliament) for decision- and policy makers on SP T3 Write the final exploitation plan | Final Exploitation plan |

RCT-Hubs: Charité, Hamburg, Freiburg, Aalborg, Wroclaw, Ghent, Catalonia, Lisbon, Bern, Zagreb; Quali-Hubs: Lisbon, Wuppertal, Oxford, Plymouth, Wroclaw, Vienna; Co-Creation-leads: Refugees/migrant: Aalborg; LGBT: Berlin; older adults: Bern

Milestones

| Nr | Milestone | Months |
| --- | --- | --- |
| 1 | Cocreated SP | 12 |
| 2 | Approval of trial by all regulatory bodies | 18 |
| 3 | First patient in | 21 |
| 4 | All qualitative interiews conducted | 32 |
| 5 | Last patient out | 54 |
| 6 | All research data published | 60 |