| Nr | Title | Begin | End | Reporting after | RCT Hub | Quali Hub | Cocr Leads |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Coordination, Project and Data Management 1 | 1 | 12 | 12 |  |  |  |
| 2 | Coordination, Project and Data Management 2 | 13 | 30 | 30 |  |  |  |
| 3 | Coordination, Project and Data Management 3 | 31 | 48 | 48 |  |  |  |
| 4 | Coordination, Project and Data Management 4 | 49 | 60 | 60 |  |  |  |
| 5 | Cocreation of Social Prescribing Intervention | 1 | 12 | 12 | Researcher 10%x12M |  | Researcher 60%x12M |
| 6 | Digital Tool Development | 1 | 18 | 30 |  |  |  |
| 7 | Digital Tool Support | 19 | 42 | 48 |  |  |  |
| 8 | Ethics and Trial Preparation | 1 | 18 | 30 | Researcher 25%x6M |  |  |
| 9 | Trial Implementation 1 | 19 | 30 | 30 | Study Nurse 60%x7M LinkWorker75%x7M Researcher 25%x12M |  |  |
| 10 | Trial Implementation 2 | 31 | 48 | 48 | Study Nurse 60%x18M Link Worker 75%x9M Researcher 25%x18M |  |  |
| 11 | Trial Analysis | 43 | 60 | 60 |  |  |  |
| 12 | Trial Process Evaluation | 13 | 48 | 48 |  |  |  |
| 13 | Health Economics Assessment | 13 | 60 | 60 |  |  |  |
| 14 | Qualitative Comparative Study | 13 | 48 | 48 |  | Researcher 60%x24M |  |
| 15 | Cointerpretation of results | 49 | 60 | 60 |  |  | Researcher 60%x12M |
| 16 | Communication, Dissemination, Exploitation, Policy 1 | 1 | 12 | 12 |  |  |  |
| 17 | Communication, Dissemination, Exploitation, Policy 2 | 13 | 30 | 30 |  |  |  |
| 18 | Communication, Dissemination, Exploitation, Policy 3 | 31 | 48 | 48 |  |  |  |
| 19 | Communication, Dissemination, Exploitation, Policy 4 | 49 | 60 | 60 |  |  |  |
| PM |  |  |  |  | 37,2 PM | 14,4PM | 14,4PM |

RCT-Hubs: Charité, Hamburg, Freiburg, Aalborg, Wroclaw, Ghent, Catalonia, Lisbon, Bern, Zagreb

Quali-Hubs: Lisbon, Wuppertal, Oxford, Plymouth, Wroclaw, Vienna

Co-Creation-leads: Refugees/migrant: Aalborg; LGBT: Berlin; older adults: Bern

Reporting Periods: 1-12; 13-30; 31-48; 49-60

# Link Working

Training 64h

| Link Working | When after t0 | Amount | Of 16 |
| --- | --- | --- | --- |
| 1st consultation | 1-2 weeks | 100% | 16 |
| 2nd consultation | 3-4 weeks | 75% | 12 |
| 3rd consultation | 5-6 weeks | 50% | 8 |
| 4th consultation | 7-8 weeks | 25% | 4 |
| 5th consultation | 9-10 weeks | 12,5% | 2 |

| Consultations | Overall | Per Month | Per Week |
| --- | --- | --- | --- |
| Per patient | 2.625 |  |  |
| Per site | 50.4 | 4.2 | 2.1 (every 2nd week) |
| Per hub | 504 | 42 | 10.5 |

+Supervision biweekly 1h
+Connecting with assets per site months -1 and +2 32h, month 2-15 16h

# Study Nurse

Training 4ßh

|  | Per patient | Per Site |
| --- | --- | --- |
| Site Initiation |  | 5h |
| Baseline | 1h |  |
| 6 months FU | 1h |  |
| 12 months FU | 1h |  |
| Monitoring in months 2-6 after site initiation |  | 2h |
| Site closing |  | 2h |

Overall 1776 patients -> in mean 178 per hub (10 hubs) and 18 per site (10 sites)  with a safe buffer: 200 per hub and 20 per site