We will also develop a web-based open-source technical solution, which will help link workers assemble, curate, and classify a list of local offerings by scraping public GIS sources. This will support link workers to select relevant offers tailored to the needs to the specific patients by using a deep-learning based language model that uses a textual description of the patient’s needs.

The AI component of the software solution will be technically robust following the seven requirements of trustworthy AI as outlined in the Assessment List for Trustworthy AI (ALTAI):

1. Human Agency and Oversight: The software will only offer suggestions to link workers. Decisions are not taken by the software but by link worker and patient together.

2. Technical Robustness and Safety: The software will run separately from the trial management being secure and resilient to attack. As an open source solution, it will be reliable and reproducible.

3. Privacy and Data Governance: No personal data will be stored. The analysis will be conducted on a server located in the EU.

4. Transparency: The software will be transparent as an open source solution. How the software works will be described in plain and easy language to link workers and patients. 5. Diversity, Non-discrimination and Fairness: The software will be co-created with participants from persons in vulnerable situations to check for non-discrimination.

6. Societal and Environmental Well-being: The software will support SP and thus have a positive environmental impact as well as a positive social impact.

7. Accountability: We will monitor and report throughout the project any negative impacts of the software and document how these can be addressed and mitigated.

We will conduct the ALTAI assessment during the development of the software to improve the trustworthiness.

[…]

| Work package number | 6 |
| --- | --- |
| Work package title | Digital Linkworking Tool Development |

Objectives To develop a web-based open-source technical solution to support link workers to deliver adapted SP. - To develop the tool based on the needs of the stakeholders - To assess the trustworthiness of the tool - To test the tool and write a documentation This WP contributes to O1, KPI1.2 and O2

Description of work Lead: Active Group T6.1 Analysis of requirements with stakeholders (mth1-2) Lead: Active Group Active Group will analyse the requirements for the linkworking tool receiving input from all partners of SP-EU. This will lead to a product backlog used in T6.2. T6.2 ALTAI-Assessment (mth3-6) Lead: Active Group Active Group will assess the digital tool by using the Assessment List for Trustworthy Artificial Intelligence. For all identified risks, measures will be taken to minimize the risk. This task will lead to D6.1. T6.3 Develop digital linkworking tool (mth2-7) Lead: Active Group Based on the product backlog from T6.1, Active Group will develop an open source linkworking tool. Active Group will set up development infrastructure including source-code management, issue tracking, and a reproducible build environment and continuous-integration proces - assemble a sample dataset for presentation in the tool, - implement a backend for the tool, and provide it with the sample dataset, - implement a frontend for linkworkers that allows finding local offerings. Parallel to the backend/frontend development, Active Group will: - implement a scraper for local offerings from public GIS sources, - implement a curation frontend for the system, - implement an AI-based curator for these sources. This task will result in a demonstrator which is D6.2. The results of T6.3 feed into T6.4 and T6.5. T6.4 Testing the linkworking tool (mth6-10) Lead: Active Group The tool developed in T6.2 will be tested iteratively with users out of the consortium. This will help to further refine the digital tool. The results of T6.3 feed into T6.4. T6.5 Documentation of the tool (mth7-12) Lead: Active Group Based on the tool developed in T6.2 and tested in T6.3, Active Group will write a documentation of the digital tool which can be used by the link workers in the RCT and then afterwards by the public. The results of T6.4 feed into WP7.

| Work package number | 7 |
| --- | --- |
| Work package title | Digital Linkworking Tool Support |

Objectives To support the use of the web-based open-source technical solution in use by link workers during the trial. - Train and support link workers to use the tool - Prepare the open source publication of the tool This WP contributes to O2.

Description of work Lead: Active Group T7.1 Develop training material on the tool for link workers (mth13-16) Lead: Active Group Based on the documentation from T6.5, Active Group will develop training material for link workers regarding the digital tool. This training material will feed into the general training material development in T8.6. Thus, this step will be closely synchronized with the partners from Plymouth and Oxford. The results of T7.1 feed then into T7.2 and T8.6 T7.2 Training and support of link workers in the RCT using the digital tool (mth16-33) Lead: Active Group Parallel to the link worker training in task T9.2 and the intervention delivery in T9.6 and T10.1, Active Group will train and support link workers in using the digital tool. This task feeds also into T7.3. T7.3 Refine digital tool (mth23-35) Lead: Active Group Based on the experiences from T7.2, Active Group will refine the digital tool. T7.3 feeds into T7.4. T7.4 Prepare the publication of the digital tool in an open repository (mth31-36) Lead: Active Group As final task in this WP, Active Group will prepare the publication of the digital tool in an open source software repository. This will include a thorough documentation of the tool. The publication will be in close alliance with the coordination and data management (WP2) and communication and dissemination (WP17) to be in line with the data management incl. FAIR principles as well as to reach the potential users of the tool. This leads to D7.1 and D7.2.

[…]

| Number | Deliverable name | Short description | Work package number | Short name of lead participant | Type | Dissemination level | Delivery date (in months) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D1.1 | Rules of Procedure | Governance document giving the rules of procedure for general assemblies, executive board and all advisory boards | 1 | Charité | OTHER | PU | 3 |
| D1.2 | Data Management Plan | The initial data management plan for the whole project | 1 | Charité | DMP | PU | 6 |
| D2.1 | Ethics Monitoring Report | Report on how ethics has been applied in all parts of SP-EU, which ethical approvals have been sought and if there are any ethical problems and how they have been mitigated | 2 | Charité | R | PU | 18 |
| D2.2 | Early-Stage Career Support Report | Report on how early-stage career researchers are and will be supported during SP-EU | 2 | Charité | R | PU | 24 |
| D3.1 |  |  |  |  |  |  |  |
| D3.2 | Gender and Diversity Report | Report on how gender and diversity are represented in consortium and project and what measures were taken to improve gender and diversity balance | 3 | Charité | R | PU | 42 |
| D4.1 | Open Science Report | Report on the implementation of open science practices throughout the project and which data has been made publicly available. | 4 | Charité | R | PU | 54 |
| D4.2 | Governance report | Report with all minutes of general assemblies conducted | 4 | Concentris | R | PU | 60 |
| D5.1 | Co-Creation Report | Report of the co-creation process to adapt the SP intervention to the needs of vulnerable groups | 5 | Aalborg | R | PU | 12 |
| D6.1 | ALTAI-Report | Assessment of the digital tool by using the Assessment List for Trustworthy Artificial Intelligence including all measures taken for identified risks | 6 | Active Group | ETHICS | PU | 6 |
| D6.2 | Prototype of Digital Tool | Prototype of Digital Tool for feedback by hubs and advisory boards | 6 | Active Group | DEM | PU | 9 |
| D7.1 | Digital Tool Documentation | Documentation of the digital tool developed to make the use as open source software widely available | 7 | Active Group | OTHER | PU | 24 |
| D7.2 | Digital Tool | The digital tool to support link worker as a open source software | 7 | AdvtiveGroup | OTHER | PU | 30 |
| D8.1 | Study Initiation Package | Study Initiation Package contains registration number of the trial, the study protocol and the regulatory and ethics approvals required for the enrolment of the first study participant | 8 | Berlin | ETHICS | PU | 14 |
| D8.2 | GP practice recruitment report | Report after full recruitment of all GP practices as study sites. Including an overview of the number of recruited sites by study hub, any problems in recruitment and, if applicable, a detailed description of implemented and planned measures to compensate for any incurred delays. | 8 | Berlin | R | PU | 18 |
| D9.1 | Midterm Recruitment Report | Report after 50% of recruited participants. Including an overview of the number of recruited participants by study sites, any problems in recruitment and, if applicable, a detailed description of implemented and planned measures to compensate for any incurred delays. | 9 | Berlin | R | PU | 23 |
| D10.1 | Final Follow-Up Report | Report after the last-patient-out of the trial.. Including an overview of the number of recruited and interviewed participants by study sites and time points, any problems in follow-up and, if applicable, a detailed description of implemented measures to compensate for any incurred delays. | 10 | Berlin | R | PU | 36 |
| D11.1 | Trial endpoint publication update | Report on the scientific publications regarding the endpoints of the trial and their status and availability as preprint | 11 | Berlin | R | SEN | 54 |
| D11.2 | Anonymized trial data | Anonymized trial data from baseline and Six-months and 12-months-follow up including extensive meta-data | 11 | Berlin | DATA | SEN | 60 |
| D12.1 | Trial Fidelity Report | Report on the fidelity of the trial | 12 | Plymouth | R | PU | 48 |
| D13.1 | Theory of Change Model | Explicated theory of change model of the intervention | 13 | Wuppertal | OTHER | PU | 18 |
| D13.2 | Health economic publication update | Report on the scientific publications regarding the health economic analysis of the trial and their status and availability as preprint | 13 | Wuppertal | R | SEN | 54 |
| D14.1 | Qualitative Recruitment Report | Report after all stakeholders for qualitative interviews have been recruited participants. Including an overview of the number of recruited participants by countries, any problems in recruitment and, if applicable, a detailed description of implemented measures to compensate for any incurred delays. | 14 | Oxford | R | PU | 32 |
| D14.2 | Qualitatiye study publication update | Report on the scientific publications regarding the comparative qualitative study and their status and availability as preprint | 14 | Oxford | R | SEN | 45 |
| D15.1 | Co-interpretation report | Report on the conducted workshops with representatives of vulnerable groups and health care providers to co-interpret the results of SP-EU | 15 | Lisbon | R | PU | 58 |
| D16.1 | Website incl. knowledge hub | A website to support communication and dissemination of SP-EU | 16 | Concentris | OTHER | PU | 3 |
| D16.2 | Communication and Dissemination Plan | The detailed preliminary communication and dissemination plan of SP-EU including target groups and communication and dissemination channels and measures | 16 | NASP | R | PU | 6 |
| D17.1 | Report on the use of communication channels | Report on the use of communication channels such as the website and social media during the first 24 months of the project | 17 | NASP | R | PU | 27 |
| D18.1 | Report on the established dissemination networks | Report on which networks for dissemination have been established in the first 36 months, e.g., with other projects funded under the same call and related European projects | 18 | Eurohealthnet | R | PU | 39 |
| D19.1 | Report on policy roundtables | Report on the national and European level roundtables, their participants and results | 19 | Eurohealthnet | R | PU | 54 |
| D19.2 | Final Exploitation Plan | Final exploitation plan to facilitate the explotation of SP-EU towards the highest possible impact after the end of the project | 19 | Eurohealthnet | R | PU | 60 |